## Notes
Numerical values on scale when zooming in
Reset original view not reset for remaining geometry when all except one is deleted
Number in OUTPUT/IGS/SURF not correct
Dependency to latest case, why do we need it? (in this case the directory was renamed then is was not possible to open bladepy due to dependency) folder
work around was to rename to old directory rename it, start bladepy and then open case in other folder then open input writer and preview the bladepro file quit bladepy, then rename the folder again
Not possible to enter more than 2 decimals for scale. In the example below the scale should be 0.5667, we clicking up and down arrows it add +1, e.g. 1,56. The step size should be smaller, perhaps +/-0.1
The RTZT output should have second input field with option between N or T (not implemented yet) not numerical values. Below in the example it is 0.00.
OK, when zoomed out.
not OK, when zoomed in.
>6 will be wrong, number in item list instead of wanted number

## Sheet3
Commit | Status | Requested Date | Complete Date | Request Description | Comments
| Not Addressed | 2017-06-01 |  | Beta angle reference type
v0.2-gf48f | Commited | 2017-09-22 | 2017-09-29 | Able to read ibl-file and plot points from iblpoints
| In progress | 2017-09-22 |  | Able to read cft-geo *cftpoints
v0.2-gf48f | Commited | 2017-09-22 | 2017-10-03 | Possibility to plot direction of point set, vector pointing direction of curve from start point (under Active 2D plot control) | Tune size
| Pending | 2017-09-22 |  | Add rotation around axis when it is implemented as a keyword in bladepro | Waiting for BladePro documents
v0.2-gf48f | Commited | 2017-09-22 | 2017-10-03 | Able to choose order for modify keywords, e.g. scale before milling or mill and then scale. (spin box?)
v0.2-gf48f | Commited | 2017-09-22 | 2017-09-29 | When opening files add filter only on *.surf.igs, *.cur.igs and *.2d.tec.dat, *points.dat,
v0.2-gf48f | Commited | 2017-09-22 | 2017-09-22 | Under general control move check box plot grid and Adjust plot to section Active 2D plot control
v0.2-gf48f | Commited | 2017-09-22 | 2017-09-29 | Put collapse possibility to all groupbox in "Properties and Tools", keeping only the transformation hidden by default
v0.2-gf48f | Commited | 2017-09-22 | 2017-09-29 | Change black color from the list to green
v0.2-gf48f | Commited | 2017-09-29 | 2017-09-29 | IBL points hidden by default

## Bugs
Revision | Status | Requested Date | Complete Date | Bug Description | Comments
v0.2-gf48f | Commited | 2017-09-22 | 2017-09-22 | Not possible to enter more than 2 decimals for scale. In the example below the scale should be 0.5667 we clicking up and down arrows it add +1, e.g. 1,56. The step size should be smaller, perhaps +/-0.1
v0.2-gf48f | Commited | 2017-09-22 | 2017-09-23 | Dependency to latest case, why do we need it? (in this case the directory was renamed then is was not possible to open bladepy due to dependency) folder
v0.2-gf48f | Commited | 2017-09-22 | 2017-10-03 | The RTZT output should have second input field with option between N or T (not implemented yet) not numerical values. Below in the example it is 0.00.
v0.2-gf48f | Commited | 2017-09-22 | 2017-10-03 | Number in OUTPUT/IGS/SURF not correct (Wrong index above 6)
v0.2-gf48f | Commited | 2017-09-22 | 2017-10-03 | Reset original view not reset for remaining geometry when all except one is deleted | Couldn't reproduce more errors like this
v0.2-gf48f | Commited | 2017-09-22 | 06/010 | Numerical values on scale when zooming in

## Potential Future Improvements
Status | Requested Date | Complete Date | Potential Improvements
Discussing | 2017-09-22 |  | Scale geometries 2D 3D, point sets
Discussing | 2017-09-22 |  | Able to show rotation axis in 3D and in meridonial view
Discussing | 2017-09-22 |  | Milling line reference
Discussing | 2017-09-22 |  | New Section in "Properties and Tools" to display milling line and rotational axis (transfering automatically to inpurt writer)